## Planned Bids 2025
APPROVED ANNUAL PROCUREMENT PLAN - 2025/2026
Name of Department/Institution: Department Of Education
Name of Provincial Treasury: LIMPOPO PROVINCIAL TREASURY
Name of Accounting Officer or Delegated Official:
Director Procurement services: Mabunda G S S
Cell no or and email address: 082 049 7346 mabundaGSS@edu.limpopo.gov.za
Date: 19 February 2025 | 2025-07-17
No | Programme | Project Description | Estimated Value (incl. taxes) | Method of procurement | Bid Specification | Approved Evaluation Criteria | Advert | Bid closing | Bid award | Value of Contract | Contract commence | Contract expiry
QUARTER ONE (APRIL - JUNE 2025)
1 | Education Management Information System | Procurement of service for a data quality audit for EMIS for 4 months |  | Bid | 2025-03-10 | 2025-03-17 | 2025-03-28 | 2025-04-22 | 2025-05-29 |  | 2025-07-01 | 2028-06-30
2 | Scholar transport | Provision of scholar transport to learners in need in the province for 3 years. |  | Bid | 2025-04-01 | 2025-04-02 | 2025-04-25 | 2025-05-19 | 2025-06-03 |  | 2025-07-01 | 2028-06-30
3 | Security Management | Contract for provision of physical security services at various Departmental sites of education in Limpopo Province |  | Bid | 2024-01-11 | 2025-11-15 | 23/02/2025 | 2025-03-13 | 17/06/2025 |  | 2025-07-01 | 31/06/2028
4 | Infrastructure | Appointment of service provider to do condition assessment for all the Public schools for the period of three (3) years |  | Bid | 2024-04-04 | 2024-04-09 | 2024-04-15 | 2024-05-16 | 2024-06-25 |  | 2024-08-01 | 2027-08-01
5 | Infrastructure | Appointment of the Suitable Construction Companies from Grade 1 to Grade 5 to render Maintenance at the Limpopo Department of Educaion Offices and schools in the Province for a period of 3 years |  | Bid | 2025-03-10 | 2025-03-12 | 2025-04-25 | 2025-05-19 | 2025-06-03 |  | 2025-07-30 | 2028-06-30
6 | TMT - Education Infrastructure Grant | David Mutshinyalo Secondary - RENOVATIONS TOILETS: 4 Seats for Boys (Enviroloo).4 Seats for Girls (Enviroloo). 2 Seats for Female Educ (Waterborne).2 Seats for Male Educ (Waterborne). COMPLETION OF NEW TOILETS: Female Educators (FSD4) – 5 Seats (waterborne).Male Educator (SM3+3UR) – 3 Seats (waterborne).Girls (F8 & FSD1) – 10 Seats (enviroloo). Boys (M4+8UR) – 4 Seats (enviroloo). EXTER WORK: Construction of 1.5m wide walkway.Construction of Septic tank. Construction of 60kl Prefabricated steel elevated tank.Installation of 77m perimeter fence |  | Bid | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-21 | 2025-04-18 |  | 2025-05-02 | 2025-11-02
7 | TMT - Education Infrastructure Grant | Magaingwana Primary - DEMOLISH PIT TOILETS:10 Seats Pit Toilets RENOVATIONS TOILETS:8 Seats Enviroloo COMPLETION OF NEW TOILETS:14 Urinals (14waterborne),(10 Enviro Loo),SD8- Waterborne-8 seats, 1 disable and 3 Urinals,The block is built up to roof level. Roofing, plumbing and complete the finishes.MD6-6 seats, 1 disable and 5 Urinals,Toilet block built up to slab. Brickwork to be built to wall plate level, install roof, toilet seats and finishes to be completed.FD4-Enviroloo,4 seats &1 disable, The block is built up to roof level. Roofing, plumbing and complete the finishes.GRADE R: GR R6-Waterborne,6 seats, 1 disable and 3 Urinals,Toilet block is built up to the slab. Walls to be built to wall plate level, install roof, toilet seats and finishes to be completed.EXTER. WORKS: Installation of 1.2m wide walkway,Fencing around Grade R toilet block, Installation of Steel palisade Fence,Painting around existing Fence perimeter,Installation of Rain harvesting tanks, Installation of 15KL Elevated Water Tanks,Completion of 1 Septic tank,Construction of 1 new septic tank |  | Bid | 2025-03-20 | 2025-02-28 | 2025-03-07 | 2025-03-28 | 2025-05-02 |  | 2025-05-14 | 2025-09-14
8 | TMT - Education Infrastructure Grant | Appointment of multi-desciplinary team professional service providers for the implementation of water,sanitation and fencing programme in Limpopo Province (46 projects) |  | Bid | 2025-03-20 | 2025-02-28 | 2025-03-07 | 2025-03-28 | 2025-05-02 |  | 2025-05-14 | 2026-11-14
9 | TMT - Education Infrastructure Grant | Geo Hydrological Investigation - Appointment of service providers for the provision of hydrogeological investigation services at various Schools in Limpopo Department of Education (27 projects) |  | Bid | 2025-03-20 | 2025-02-28 | 2025-03-07 | 2025-03-28 | 2025-05-02 |  | 2025-05-14 | 2026-11-14
10 | TMT - Education Infrastructure Grant | Mosepedi Secondary - Renovations of ENVIROLOO toilets 20 x seats , construction of waterborne 5 x seats, 1 x Paraplegic toilets and 2 x Urinals . New septic tank and french drain, fencing around water tanks, new 2x 10kl water tank + steel structure, steel palisade fence, 3 x drinking water fountains, Water reticulation. |  | Competitive bid | 2025-08-15 | 2025-09-11 | 2025-09-25 | 2025-10-16 | 2025-11-23 |  | 2025-11-30 | 2026-01-29
11 | Infrastructure | Matamela Ramaphosa secondary school:Construction of 30 ordinary classrooms, large administration block, nutrition block, multi-purpose hall, computer laboratory and media additional toilets, additional multipurpose classroom, borehole and elevated storage tank of 100kl capacity, steel palisade fence 2.1m high, guardhouse, 25 covered parking bays, 15 uncovered parking bays, sports fields, assembly area |  | Bid | 2025-03-20 | 2025-03-30 | 2025-04-01 | 2025-05-01 | 2025-07-30 |  | 2025-08-04 | 2027-09-30
QUARTER TWO (JULY -SEPTEMBER 2025)
12 | IN-School Sports Arts, & Culture | Appointment of the service provider for uniform & clothing and sports equipment for school sport activities for public ordinary and public special school for 3 years |  | Bid | 2025-05-10 | 2025-05-17 | 2025-06-28 | 2025-07-22 | 2025-08-29 |  | 2025-09-01 | 2028-08-31
13 | Security Management | Maintenance contract of Access control system and CCTV for a period of 3 years |  | Bid | 2025-05-10 | 2025-05-17 | 2025-06-28 | 2025-07-22 | 2025-08-29 |  | 2026-01-09 | 2028-08-31
14 | MST Directorate | Provision of overhead projectors and visualizers to schools and officials |  | Bid | 2025-05-31 | 2025-04-05 | 2025-06-25 | 2025-07-19 | 2025-08-01 |  | 2025-09-01 | 31/08/2028
15 | MST Directorate | Provision of tablets and learning management system (e-Education platform) to schools for a period of three (3) years |  | Bid | 2025-05-31 | 2025-04-05 | 2025-06-25 | 2025-07-19 | 2025-08-01 |  | 2026-09-01 | 31/08/2028
16 | MST DIRECTORATE | Appointment of a service provider who will procure and distribute learning and teaching support materials such as Mathematics, Sciences, Technology worshop and laboratory equipment, machinery, tools, consumables and aparatus, ICT reources and software and coding and robotics resources. |  | Bid | 2025-05-08 | 2025-05-08 | 15/08/2025 | 15/09/2025 | 31/10/2025 |  | 2025-01-11 | 31/03/2026
17 | Infrastructure | Appointment of the Suitable consulting team to be the Infastructure Technical Resource Unit for the period of three (3) years.Limpopo Daprmnet of Education Infrasutructure Unit |  | Bid | 2025-05-10 | 2025-05-12 | 2025-06-25 | 2025-07-19 | 2025-06-08 |  | 2025-09-30 | 2028-08-31
18 | Infrastructure | Appointment of service providers to manufacture , supply and delivery of mobile classrooms for a preiod of 3 years |  | Bid | 2025-05-01 | 2025-05-02 | 2025-06-25 | 2025-07-19 | 2025-06-08 |  | 2026-01-09 | 31/08/2028
19 | Infrastructure | APPOINTMENT OF PROFESSIONAL SERVICE PROVIDERS TO UNDERTAKE IMPLEMENTATION OF VARIOUS INFRASTRUCTURE PROJECTS IN MECHANICAL/ELECTRICAL/PROJECT MANAGEMNT AND HEALTH AND SAFETY SRVVICES FOR THE LIMPOPO DEPARTMENT OF EDUCATION THROUGHOUT THE LIMPOPO PROVINCE FOR A PERIOD OF 36 MONTHS |  | Bid | 2025-01-20 | 2025-01-30 | 2025-02-01 | 2025-03-01 | 2025-05-30 |  | 2025-05-30 | 2028-05-30
20 | ICT | Provisioning of ICT Infrastructure (Servers, wireless network and etc) to circuit office |  | SITA RFB 2003 | 2025-05-10 | 2025-05-17 | 2025-06-10 | 2025-07-21 | 2025-08-29 |  | 2025-06-01 | 2028-09-30
21 | ICT | ICT Infrastructure Revamp (Head office and District offices) |  | SITA | 2025-05-10 | 2025-05-17 | 2025-06-10 | 2025-07-21 | 2025-08-29 |  | 2025-06-01 | 2028-09-30
22 | ICT | Management of ICT Security |  | SITA tender 1138 | 2025-05-10 | 2025-05-17 | 2025-06-10 | 2025-07-21 | 2025-08-29 |  | 2025-09-01 | 2028-09-30
23 | ICT | Appointment of a service provider to develop and provide support for Online Learner Admission System for a period of 3 years |  | SITA tender 1138 | 2025-05-30 | 2025-05-07 | 2025-06-13 | 2025-07-13 | 2025-08-30 |  | 2025-09-01 | 2028-06-30
24 | TMT | Appointment of a multi- disciplinary team of professional service providers (PSP) for the implementation of water, sanitation and infrastructure at Mosepedi secondary school |  | Bid | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-09-05 | 2025-09-08 |  | 2025-10-03 | 2027-04-02
QUARTER THREE (OCTOBER-DECEMBER2025)
The Accounting Officer/ Authority declares that he/she has engaged with the Executive Authority who concurs with and has approved this Procurement Plan
Acting Accounting Officer/Authority Mr Mashaba K.M |  |  | DATE
_________________________________________ |  |  | ________________________________
Formulas:
Approved Evaluation Criteria = +[Bid Specification]+27
Advert = +[Approved Evaluation Criteria]+14
Bid closing = +[Advert]+21
Bid award = +[Bid closing]+38
Contract commence = +[Bid award]+7
Contract expiry = +[Contract commence]+60